## Sheet1
Bake biggest chocolate chip cookie in the world
Tasks | Start Date | Days Needed | Completion | Adjusted Length
Secure location | 2023-08-01 | 15 | 2023-08-22 | 21
Order ingredients | 2023-08-01 | 30 | 2023-09-12 | 42
Notify Guinness World Records | 2023-08-15 | 5 | 2023-08-22 | 7
Invite press & participants | 2023-09-10 | 10 | 2023-09-22 | 12
Build solar reflecting oven | 2023-09-05 | 8 | 2023-09-15 | 10
Final prep | 2023-09-20 | 7 | 2023-09-29 | 9
Event day | 2023-10-01 | 1 | 2023-10-02 | 1

## Sheet2
Project Name
Project Start | 2025-04-01
Current Date | 2025-04-20
Weeks in progress | 3
[5 empty] | 2025-04-01 | 2025-04-08 | 2025-04-15 | 2025-04-22 | 2025-04-29 | 2025-05-06 | 2025-05-13
Task | Start date | End date | Days | Progress | 1 | 2 | 3 | 4 | 5 | 6 | 7
Planification
Etude de marche | 2025-04-01 | 2025-04-07 | 6 | 100%
Realisation du cahier des charges | 2025-04-01 | 2025-04-07 | 6 | 100%
les masuettes | 2025-04-01 | 2025-04-07 | 6 | 100%
Développement Backend
Authentification | 2025-04-06 | 2025-04-27 | 21 | 10%
API | 2025-04-06 | 2025-04-27 | 21 | 10%
Intergation du paiement | 2025-04-06 | 2025-04-27 | 21 | 0%
Développement Frontend
Intégration du design | 2025-04-21 | 2025-05-05 | 14 | 10%
Task 2 | 2025-04-21 | 2025-05-05 | 14 | 0%
Tests & Déploiments
Tests unitaires | 2025-05-05 | 2025-05-12 | 7 | 0%
Déploiment cloud | 2025-05-05 | 2025-05-12 | 7 | 0%